Department of Applied Data Science

DATA 298A MSDA Project I

Progress Report 2

# Team Number: 2 (Topic 23: Low-Resource and Code-Switched Language Systems)

# Members: Savalia, Jenil; Shevkar, Yash; Singh, Prakhar; Thomas Lnu, Shibin; Waghmare, Sarvesh

# Date of Report: October 22, 2026

# Cycles covered: Cycles 2 and 3, 25 September to 22 October 2026

# Part A    Project Status

| Item | Planning | Investigation | Complete | Document |
| --- | --- | --- | --- | --- |
| 1. Introduction |  |  |  |  |
| 1.1 Project Background and Executive Summary | 100% | 95% | 95% | 95% |
| 1.2 Project Requirements | 100% | 95% | 95% | 95% |
| 1.3 Project Deliverables | 100% | 90% | 85% | 85% |
| 1.4 Technology and Solution Survey | 100% | 95% | 95% | 95% |
| 1.5 Literature Survey of Existing Research | 100% | 95% | 95% | 95% |
| 2. Data and Project Management Plan |  |  |  |  |
| 2.1 Data Management Plan | 100% | 90% | 90% | 85% |
| 2.2 Project Development Methodology | 100% | 95% | 90% | 95% |
| 2.3 Project Organization Plan | 100% | 95% | 90% | 95% |
| 2.4 Project Resource Requirements and Plan | 100% | 85% | 60% | 90% |
| 2.5 Project Schedule | 100% | 90% | 85% | 90% |
| 3.1 Data Process | 100% | 95% | 95% | 35% |
| 3.2 Data Collection | 100% | 95% | 95% | 40% |
| 3.3 Data Pre-processing | 100% | 95% | 95% | 35% |
| 3.4 Data Preparation | 100% | 95% | 95% | 40% |
| 3.5 Data Transformation | 100% | 90% | 90% | 35% |
| 3.6 Data Statistics | 100% | 95% | 95% | 50% |
| 4.1 Model Proposals | 100% | 90% | 85% | 90% |
| 4.2 Model Supports | 90% | 70% | 55% | 40% |
| 4.3 Model Comparison and Justification | 100% | 85% | 70% | 85% |
| 4.4 Model Evaluation Methods | 100% | 90% | 85% | 85% |
| 4.5 First Model Implementation | 85% | 60% | 25% | 20% |
| 4.6 Baseline Reproduction | 80% | 55% | 10% | 20% |
| 5. Prototype and System Implementation | 60% | 25% | 5% | 5% |
| 6. Benchmarking, Evaluation, and Failure Study | 55% | 30% | 15% | 10% |
| 7. Reproducibility | 100% | 90% | 85% | 60% |
| 8. 298B Plan | 55% | 25% | 10% | 5% |
| References | 100% | 90% | 95% | 95% |

Template rows 2.2 to 2.5 follow the department numbering. Their values come from the team's workbook sections: 2.2 Project Management Plan (2.2.1 to 2.2.8, which covers methodology and organisation) for rows 2.2 and 2.3, 2.3 Resources for row 2.4, and 2.4 Schedule for row 2.5. Rows 4 to 8 are added below the template's rows. All values were checked against main at commit b480fa6 (Part A, Linear 298-46, owner Sarvesh).

## Explanation for the large gaps

Rows 3.1 to 3.6 — Data Engineering. Complete is 90–95%, Document is 35–50%, a gap of 45 to 60 points on every row.

This is the one place in the project where the engineering has run ahead of the writing, and the reason is scheduling rather than neglect. The four-stage pipeline is merged (scripts/run_pipeline.py, src/lrcs/), has been run end to end on the real HinGE corpus in 11.96 seconds, and its outputs are committed: reports/data_statistics.json, data/processed/manifests/hinge_split_manifest.json, the four EDA figures under reports/figures/, two run records under runs/, and a 48-cell demonstration notebook. The test suite covering it reports 27 passing tests.

What does not exist is the Section 3 prose. Sections 3.1 to 3.6 belong to Workbook 2, which is due 11 November, and the writing is filed as 298-57 with a 6 November date. Writing it now would mean writing Workbook 2 content into a progress report.

The numbers that section will carry are already measured and committed, so this is a documentation lag against a known date, not unfinished work:

• 1,976 source rows yielding 4,799 human references, measured off the file against 4,803 reported in the source paper

• six cleaning filters removing 125 records, each removal charged to the filter that rejected it, leaving 4,674

• 1,938 unique sources grouped into 1,937 near-duplicate clusters

• splits of 3,738 / 468 / 468 with zero exact and zero near-duplicate overlaps across all split pairs

• CMI 25.3, Switch-Point Fraction 0.240, M-index 0.693, 86.1% of sentences code-mixed, at 68.2% tagger coverage

No other row differs by more than 40 points. Row 2.4 (template numbering; workbook 2.3) runs the other way — Document 90% against Complete 60% — because the resource plan is fully written while the GPU allocation it depends on is still unconfirmed. That is a 30-point difference and is tracked as a blocker in Part D rather than as a documentation gap.

## Rows that are deliberately low

Three rows would be easy to overstate, and are not.

4.5 First Model Implementation, Complete 25%. models/generate_zeroshot.py and models/train_qlora.py are merged and their CPU paths are tested, and runs/ now holds four model records from a Tesla T4. But no model has been trained on the real corpus and no scored run exists at three seeds: those four records are a single-seed smoke test on synthetic data with a 0.5B stand-in model, and docs/COMPUTE_BUDGET.md states in terms that none of it is a reportable result. Issues 298-24 and 298-25 were previously marked Done without a result and were reset to In Progress on 23 October under 298-45. The scored run is 298-53, due 3 November, and the QLoRA fine-tune at three seeds is 298-54, due 9 November. Both are blocked on GPU confirmation (298-51).

4.6 Baseline Reproduction, Complete 10%. The target is fixed and justified — Gahoi et al. (2022), Table 2, ROUGE-L 0.617 — and evaluation/run_eval.py --check-baseline enforces the 0.01 tolerance. But the reproduction has not been run, and the authors released no code, so the mBART recipe is being rebuilt from the paper description. That work is 298-52, due 7 November.

5 Prototype and System Implementation, Complete 5%. Nothing is deployed. The serving stack is chosen and the requirements carry a numeric latency target, but Team Meeting 2 on 12 November requires a live prototype and there is none today. That is 298-56.

## Method

Percentages were assigned against four questions, applied row by row:

• Planning — is the approach decided and recorded somewhere a reader can check?

• Investigation — has the reading and experimentation behind it been done?

• Complete — does the artifact exist on main and run?

• Document — is the report prose for that section written?

A row was only marked above 80% on Complete if an artifact exists on main that a reader can open. Issues marked Done on the Linear board without a corresponding artifact were treated as incomplete. Eight such issues were found and reset on 23 October under 298-45 — 298-10, 298-15, 298-16, 298-17, 298-21, 298-23, 298-24 and 298-25 — so that Part C, this table and the repository agree with each other. The audit is recorded in docs/progress2/board_reset_298-45.md.

# Part B   Minutes of Meetings

| Time and Date: Team Meeting 1 (graded checkpoint) on 10/08/2026 |  |  |  |
| --- | --- | --- | --- |
| Location/media: Online/Zoom |  |  |  |
| Participants: Savalia, Jenil; Shevkar, Yash; Singh, Prakhar; Thomas Lnu, Shibin; Waghmare, Sarvesh; instructor and ISA |  |  |  |
| Section | Achievements | Issues | Recommended Solutions |

| 1.1 |  |  |  |
| --- | --- | --- | --- |
| 1.2 |  |  |  |
| 1.3 |  |  |  |
| 1.4 | - Every model identifier verified against its official Hugging Face model card on 8 Oct, with the command to repeat the check. Closes the Progress Report 1 issue of a draft naming a configuration that does not exist | Instructor and ISA: review the work presented, do more research, find more research papers, and implement accordingly | Review 1.4 against recent code-switching MT work. Add the papers that change a design decision and implement what they change (Jenil, all members) |
| 1.5 |  | - Literature base too narrow for the design decisions it supports (instructor and ISA feedback) | - Extend 1.5 with recent code-switching MT and evaluation papers, and carry the findings into the pipeline, harness and models |
| 2.1 |  |  |  |
| 2.2 |  | Issues marked Done on Linear with no artifact on main No branch protection; no merged PR has a recorded review | Reset each to its true state with a comment saying what is missing (298-45, Prakhar) Protection requiring one non-author approval, plus a reviewer rotation (298-60, Prakhar) |
| 2.3 |  |  |  |
| 2.4 |  | GPU allocation unconfirmed since 26 Sep | Written answer from the cluster, or fund the fallback (298-51, Prakhar) |
| 2.5 |  |  |  |
| 3.1 | - Four-stage pipeline (ingest, clean, split with leakage gate, statistics) merged and run live; fresh-clone preflight logs in reports/rehearsals/2026-10-07/ - Leakage gate demonstrated halting on an injected test source |  |  |
| 3.2 | - 4,799 references measured directly off the file, against 4,803 published; both reported in docs/datasheet.md. Closes the PR1 issue of an uncorroborated count | Reconciliation of the four-reference difference still open | Recount from Table 1 of the source paper; report both until settled (Yash) |
| 3.3 |  |  |  |
| 3.4 | - Splits re-derived from 1,938 unique sources: 0 exact and 0 near-duplicate overlaps at Jaccard >= 0.7; 3,738 / 468 / 468 committed with SHA-256 manifests. Closes the PR1 issue that HinGE's released splits are not mutually exclusive | Gold test set holds 0 of 800 items, so the +3 chrF++ criterion cannot be evaluated | Author and validate the first 200 items; cut 800 to 500 under the recorded rule if throughput is too low (298-55, Jenil, 5 Nov) |
| 3.5 |  |  |  |
| 3.6 | - Corpus statistics committed (reports/data_statistics.json); real-corpus run records dated 8 Oct under runs/ |  |  |
| Reference |  |  |  |

| Time and Date: Progress Report 2 working session on 10/22/2026 |  |  |  |
| --- | --- | --- | --- |
| Location/media: Online |  |  |  |
| Participants: Savalia, Jenil; Shevkar, Yash; Singh, Prakhar; Thomas Lnu, Shibin; Waghmare, Sarvesh |  |  |  |
| Section | Achievements | Issues | Recommended Solutions |
| 1.1 |  |  |  |
| 1.2 |  |  |  |
| 1.3 |  |  |  |
| 1.4 |  |  |  |
| 1.5 |  |  |  |
| 2.1 | - Data management plan merged (PR #26, Yash), closing the overdue 298-35 |  |  |
| 2.2 | - Part A status (PR #24, Sarvesh) and Part D risks (PR #28, Shibin) written from repository evidence | No commits between 9 and 21 October; Cycle 3 at 0 of 13 points after ten days 8 Oct minutes written up 14 days late, against the 24-hour rule Zero reviews on PRs #21 to #27; six self-merged Eight issues Done on the board without artifacts | Every member commits against a cycle-4 issue by 26 Oct, then at least twice a week; Prakhar checks the log weekly Recorder commits minutes to docs/minutes/ the same day (Jenil) Branch protection and reviewer rotation by 26 Oct (298-60) Reset 298-10, -15, -16, -17, -21, -23, -24, -25 today (298-45) |
| 2.3 |  |  |  |
| 2.4 |  | No GPU allocation: blocks the baseline, M1 and M2 | Written answer, or the fallback funded and one job run on it, by 24 Oct (298-51, Prakhar) |
| 2.5 |  | Team Meeting 2 on 12 Nov needs a cloud pipeline, a live prototype, the baseline reproduced and a first model trained; none exists; three days of slack | Cycle 4 plan: GPU 24 Oct (298-51), M1 scored 3 Nov (298-53), baseline 7 Nov (298-52), M2 and prototype 9 Nov (298-54, 298-56) |
| 3.1 |  |  |  |
| 3.2 |  |  |  |
| 3.3 |  |  |  |
| 3.4 |  | Gold set still 0 of 800 | First 200 items authored and validated, plus the 50-item rater pilot, by 5 Nov (298-55, Jenil) |
| 3.5 |  |  |  |
| 3.6 |  |  |  |
| 4.5 | - QLoRA trainer and Colab notebook for M1 and M2 merged (PRs #25, #27, Sarvesh); first GPU smoke runs under runs/, on a free T4 and synthetic data. Not reportable results (docs/COMPUTE_BUDGET.md) | No model trained or scored on the real corpus | M1 on three seeds by 3 Nov (298-53); M2 QLoRA on three seeds by 9 Nov (298-54) |
| 4.6 |  | Baseline not reproduced; Gahoi et al. (2022) released no code | Rebuild the recipe and run both input conditions by 7 Nov (298-52, Shibin) |
| Ref |  |  |  |

# Part C   Work Completed

Linear 298-48. Owner: Prakhar; completed by Sarvesh on 22 October while Prakhar was unavailable. Reporting period: Cycles 2 and 3, 25 September to 22 October 2026, Pacific time.

Pacific time is stated because it changes the counts. Linear anchors its cycle boundaries to Pacific midnight and the Canvas deadline is Pacific, but the GitHub API reports UTC, which pushes work done on a California evening into the next day. Five pull requests merged on the evening of 24 September — #1, #2, #3, #5 and #6 — and three issues closed with them (298-12, 298-14, 298-18) read as 25 September in UTC. They belong to Progress Report 1, whose window closed on 24 September, and counting them here would report the same work twice. They are excluded.

This part must agree with the Linear board, and the board is what gets checked. It was written after the 298-45 reset, so the counts are counts of work a reader can open, not of issues someone marked Done. The audit is in docs/progress2/board_reset_298-45.md.

Two columns are given because they disagree, and the disagreement is the point. Issues closed is the Linear board. PRs merged is the GitHub author of the branch that landed the code. Where one member owns an outcome and another writes it, the board records the first and GitHub the second.

| Member | Issues closed | Points | Linear issue IDs | Labels worked | PRs merged | Key artifact |
| --- | --- | --- | --- | --- | --- | --- |
| Waghmare, Sarvesh | 5 | 15 | 298-30, 298-31, 298-36, 298-39, 298-46 | eval, writing | 11 — #31, #27, #25, #24, #16, #15, #14, #13, #9, #8, #7 | QLoRA trainer, Colab notebook and the first GPU run records (PRs #25, #27) |
| Singh, Prakhar Kumar | 4 | 12 | 298-37, 298-40, 298-45, 298-48 | infra, writing | 2 — #20, #17 | Demo runbook and two fresh-clone preflight records (PR #20) |
| Savalia, Jenil Sanjaybhai | 4 | 11 | 298-32, 298-42, 298-43, 298-47 | writing | 7 — #30, #29, #23, #22, #19, #18, #12 | Minutes for Team Meeting 1 and the 22 Oct session — docs/minutes/ (PR #29) |
| Thomas Lnu, Shibin Biji | 4 | 11 | 298-33, 298-41, 298-44, 298-49 | data, writing | 2 — #28, #21 | Part D blockers and critical path — docs/progress2/part_d_risks.md (PR #28) |
| Shevkar, Yash | 3 | 16 | 298-34, 298-35, 298-38 | data, research, writing | 1 — #26 | Four-stage data pipeline, one command (PR #18 branch yash/298-38), and section 2.1 (PR #26) |
| Team total | 20 | 65 | — | 5 of 6 labels | 23 | — |

Repository: https://github.com/298A-Team-2-Topic-23/Low-Resource-and-Code-Switched-Language-Systems

## Reconciliation notes

• Eight issues were reset from Done before this table was counted, because no artifact existed on main: 298-10, 298-15, 298-16, 298-17, 298-21, 298-23, 298-24 and 298-25. Each carries a comment naming what is missing and the issue that now tracks it. Progress Report 1 scored in the bottom band on exactly this criterion, so this was the most important piece of work in this part.

• Prakhar's four closed issues overstate his contribution this period, and his two pull requests understate it. He was ill on 22 October. 298-45 and 298-48 are assigned to him and closed under his name, but the work was done by Sarvesh and landed as PR #31 — which is why Sarvesh's eleven pull requests include it. His real output this period is 298-37 and 298-40, both merged 7 October. Stated plainly rather than left for a grader to notice.

• Assignee and author disagree in both directions. 298-34 and 298-38 are Shevkar's on the board and landed as PRs #19 and #18 authored by Savalia; that is why Shevkar shows 16 points against one pull request — the data pipeline alone (298-38) is eight points. PRs #15 and #16 run the other way, carrying Thomas Lnu's branch names but committed and merged under Waghmare's account. Neither column alone is honest, which is why both appear.

• Points and issue counts rank the team differently and neither is a ranking. Shevkar closed the fewest issues and the second-most points; Waghmare closed the most issues and fewer points than Shevkar. Reading either column as a league table would be wrong.

• No model-labelled issue closed this period. Five of the six configured labels were exercised — data, eval, infra, research, writing. The sixth is model, and its two open issues (298-53, 298-54) are both In Progress and blocked on the GPU allocation. The label gap and Part A row 4.5 say the same thing: no model has been trained.

• Work landed on two days. All 23 merges fell on 7 October and 22 October. Nothing reached main between 8 and 21 October — one of the cycles before Team Meeting 2 produced no repository work at all. Tracked as blocker 7 in Part D.

• No merged pull request in this window carried a review, and 19 of the 23 were merged by their own author. Branch protection is not enabled; the protection endpoint returns "Branch not protected". Individual contribution is graded off the Linear-to-GitHub chain, so unreviewed self-merges are weak evidence for every member, not only for the authors. Tracked as 298-60, due 26 October. PR #31, which carried the reset and this file, was itself self-merged — the problem is live, not historical.

• The reset made the cycle look worse, which is correct. Cycle 3 (12 to 26 October) now carries 22 issues and 77 points, of which 9 issues and 24 points are Done. Before the reset it read 14 issues and 43 points: returning the eight falsely-Done issues added 33 points of real unfinished work. The cycle will miss its scope, and that is stated here rather than absorbed.

# Part D   Blockers, Risks and Next Period

Linear 298-49. Owner: Shibin. Reporting period: Cycles 2 and 3, 25 September to 22 October 2026.

Every blocker below was checked against main at commit 30fc77c, the GitHub pull-request record and the Linear board on 22 October. Where a claim could not be checked it is not made.

## The binding constraint

Three weeks remain before Team Meeting 2 on 12 November, and that date cannot move: a missed graded session scores zero. The checkpoint requires four things — a cloud pipeline, a live prototype, the published baseline reproduced, and the first model trained. None of the four exists today. Every blocker below is ranked by how directly it stands between the team and those four items.

The critical path is short and has almost no slack:

GPU confirmed (24 Oct) -> M1 scored (3 Nov) -> M2 trained (9 Nov) -> deployed (9 Nov) -> TM2 (12 Nov)

baseline reproduced (7 Nov) ------------------------------^

Three days separate the last planned delivery from the checkpoint. A slip of more than three days on any node on that path lands on the demo.

## Blockers

| # | Blocker | Evidence | Impact | Owner | Next action and date |
| --- | --- | --- | --- | --- | --- |
| 1 | No GPU allocation | Requested 26 Sep; still unconfirmed. The only GPU runs so far used a free Colab Tesla T4 | Blocks the baseline, M1 and M2 — three of the four Team Meeting 2 items | Prakhar | Written answer from the cluster, or the fallback funded and one job run on it, by 24 Oct (298-51) |
| 2 | No model trained on the real corpus | runs/ holds four model records, all smoke tests on synthetic data with a 0.5B stand-in (docs/COMPUTE_BUDGET.md: "None of it is a reportable result"). 298-24 and 298-25 were marked Done without artifacts | Section 4.5 cannot progress; the first-trained-model requirement for 12 Nov is unmet | Sarvesh | M1 scored on three seeds by 3 Nov (298-53); M2 QLoRA on three seeds by 9 Nov (298-54) |
| 3 | Baseline not reproduced | Gahoi et al. (2022) released no code. 298-15 and 298-16 were marked Done without artifacts and are being reset | This is the project's quality gate: until the harness reproduces a published number, no model result can be interpreted | Shibin | Recipe rebuilt and run under both input conditions by 7 Nov (298-52) |
| 4 | Harness gaps that affect that gate | evaluation/run_eval.py has no bootstrap resampling, although requirement AI-2 commits to it. Its regex normalisation fully collapses only 3 of the 72 groups in analysis/spelling_variants.tsv, and two rules corrupt words (hy→y, hna→na). ROUGE-L and WER are computed on the normalised tokens | No M1-versus-M2 difference can be called significant; the raw-versus-normalised gap measures little; and the baseline is scored on a different tokenisation from the paper's | Shibin | Bootstrap and lexicon-driven normalisation, with a test that fails on the regex version, by 2 Nov (298-59) |
| 5 | Gold set at 0 of 800 items | data/goldtestset/gold_set.csv holds no rows | Success criterion AI-1 is defined on this set; without it there is no surface to report the headline result on | Jenil | First 200 items authored and validated by 5 Nov (298-55); 800-to-500 fallback rule stays in force |
| 6 | No code review on any merge this period | All 23 pull requests merged in the window carry zero reviews, and 19 of the 23 were merged by their own author. main is unprotected: the protection endpoint returns "Branch not protected". PR #31, which carried the board reset and Part C, was itself self-merged, so this is live rather than historical | The Linear-to-GitHub chain is how individual contribution is graded; unreviewed self-merges are weak evidence for every member | Prakhar | Branch protection on and a reviewer rotation published by 26 Oct (298-60). Every PR after that date carries one non-author approval |
| 7 | No commits from 8 to 21 October | git log shows the last commit on 7 Oct and the next on 22 Oct | One of the six cycles before the checkpoint produced no repository work | All five; Prakhar tracks | Every member pushes at least one commit against a cycle-4 issue by 26 Oct, then at least twice a week; Prakhar checks the commit log at each weekly meeting |
| 8 | Issues marked Done without artifacts — resolved 22 Oct | Eight issues were Done with no linked PR or run: 298-10, 298-15, 298-16, 298-17, 298-21, 298-23, 298-24 and 298-25. All eight were reset on 22 Oct and each carries a comment naming what is missing (docs/progress2/board_reset_298-45.md) | Resolved. Part A, Part C and the board now agree. The cost is visible: Cycle 3 went from 43 to 77 points of scope | Prakhar (executed by Sarvesh) | Closed (298-45). The standing rule is now Closes 298-NN in the landing commit, not Refs |

## Risks not yet blocking

| Risk | Likelihood / impact | Trigger | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| The baseline cannot reach 0.617 even if rebuilt correctly | High / high | Reproduction lands below 0.60 | The published 0.617 comes after an automatic transliteration step and a dictionary-based step whose dictionary was not released; with automatic transliteration alone the paper reports 0.484. Report against both rows, check tokenisation first, and raise the tolerance question with the advisor rather than tune toward the number | Shibin |
| MixMT Subtask-1 test references not obtainable | Medium / high | Codalab download unavailable by 26 Oct | Fall back to the held-out human split of HinGE, as the abstract already states, and say so in the report | Shibin |
| Free-tier GPU is too slow for three seeds of a 7B model | High / medium | One M2 seed takes more than a session | The Colab notebook already persists finished seeds; reduce to a 4B-class backbone only as the plan's stated last resort, never below three seeds for reported results | Sarvesh |
| Zero-shot output in the wrong script | Observed / medium | The 0-shot smoke run produced Devanagari in 13 of 48 outputs | Count it as a failure-taxonomy category rather than filter it; compare against 5-shot, which produced none | Sarvesh |
| Back-translation leaks the test set | Medium / high | HinGE's English comes from the IIT Bombay corpus, which is part of Samanantar | Run the contamination check before any synthetic data is generated (298-58, 9 Nov) | Yash |
| Model scripts disagree on the default backbone | Low / medium | A command-line run omits --model | generate_zeroshot.py defaults to Qwen3-8B and train_qlora.py to Qwen2.5-7B-Instruct; the Colab notebook passes Qwen2.5-7B-Instruct to both, so the planned runs agree. Align the defaults when either script is next touched | Sarvesh |

## Outcomes for the next period

Cycle 4 runs from 22 October to 9 November, ending three days before Team Meeting 2. Five outcomes define success for it. Each is a Linear issue with one owner and a date, and each is checkable against an artifact rather than a statement.

| # | Outcome | Issue | Owner | Due | Done means |
| --- | --- | --- | --- | --- | --- |
| 1 | GPU access confirmed or the fallback funded and tested | 298-51 | Prakhar | 24 Oct | A run record from the chosen GPU in runs/ |
| 2 | Published baseline reproduced, or the failure reported with evidence | 298-52 | Shibin | 7 Nov | Scored outputs for both input conditions and a --check-baseline result |
| 3 | Model 1 zero-shot scored on three seeds | 298-53 | Sarvesh | 3 Nov | Three run records and a results row with mean ± std |
| 4 | Model 2 QLoRA trained and scored on three seeds | 298-54 | Sarvesh | 9 Nov | Three adapters' run records and a results row with mean ± std |
| 5 | First 200 gold items authored and validated | 298-55 | Jenil | 5 Nov | validate_gold_set.py --expected-count 200 passes |

Supporting the five, and needed for the same checkpoint:

| Issue | What | Owner | Due |
| --- | --- | --- | --- |
| 298-50 | Progress Report 2 assembled and submitted | Jenil | 22 Oct |
| 298-56 | Thin-slice prototype deployed to the cloud for the live demo | Prakhar | 9 Nov |
| 298-57 | Workbook 2 sections 3.1–3.6 written from the real run | Yash | 6 Nov |
| 298-58 | Back-translation source prepared and contamination-checked | Yash | 9 Nov |
| 298-59 | Bootstrap and lexicon-driven normalised chrF++ in the harness | Shibin | 2 Nov |
| 298-60 | Branch protection and reviewer rotation | Prakhar | 26 Oct |

## What would change this plan

• No GPU by 24 October moves the baseline, M1 and M2 onto the fallback the same day, and the team reports at the next meeting whether three seeds still fit before 9 November.

• A baseline that misses tolerance is reported as a finding with evidence. Model results are then presented as uninterpreted measurements, and that limitation is stated at Team Meeting 2 rather than discovered there.

• Gold-set throughput below 200 items by 5 November triggers the recorded 800-to-500 fallback, and M1/M2 are scored on the HinGE test split in the meantime.